## Index
Sr No | Sheet Name
1 | Queries
2 | Existing System BD
3 | PSU & Printer Board
4 | MB and Conn Card
5 | Display and Incubator
6 | New system Build
7 | HW BreakDown
8 | WBS
9 | Microcontroller
10 | 80C188EB-20
11 | BD + Power Sch
12 | STM32F767ZIT6mapping
13 | ADC
14 | Memory
15 | Eth_Phy
16 | Design Decision

## Queries
Back
| Sr No. | Questions - Descriptions | Meril remark @19/Nov | Rezonet remark @21/Nov
| 1 | Can you pls help with ref Sch for MB board. Could help us to understand more on the interfaces and functionality required. | Yes, R & D will provide by this week.. | Thanks Noted
| 2 | It seems Printer Driver board is sourced from CHINA. Do we expect to make in India or locally design? | We have our own design for Printer board and source code, we will provide Sch | Thanks Noted
| 3 | Incubator & heater section - Could you pls share it sch and Mechanical details. We need to know how the temp is monitored / observed | Yes, we will explain but is very simple closed loop hardware with TIP 122 Temp. sensor… | Noted Thanks, We shall wait for required inputs
| 4 | Does it required to have features like USB OTG, Ethernet, WiFi, BLE etc. | Ethernet is not required for semi auto, but I it doesn’t impact cost for adding, Pls. add | Noted Ethernet - Not needed for Semi. But Provision could be there.
| 5 | Does it required to have any sub tests undert PT, APTT, TT, FIB testing. Any feature enhanments is expected here. | Yes, Many more test has to be add like F7,F8,F10 &F12 etc. which Meril will take care | Thanks Noted
| 6 | Could you pls help with the unit calibration process or configuration process if any. | in the exsisting Machine have Photometer( ADC) , offset and Temp. Adjustment | Thanks Noted

## Existing System BD
Back
Exising - System Interface Details

## PSU & Printer Board
Back
| Power Card |  | Power Card Block Diagram | Input Power supply
| 1 | The power card's bottom side has multiplelinks; we need to redesign the PCB.
| 2 | In the power card, replace the L7912CV, L7812CV, and L7905CV THT regulators with more efficient alternatives.
Meril Remarks:1) Meril has designed improved Power supply PCB with SMD Vol regulator IC, so if you can assist same then ok otherwise for new Micro controller Board, make New PCB as per requirement. 2) It is recommended to use same Power supply +15V,- 15V ,6A or else you can suggest - Noted thanks
Printer Board

## MB and Conn Card
Back
| MicroController Board |  |  |  | Connector Card
Key BOM
| MFR PN | Description | Manufacturer | Status
| hm628128blfp-7 | Standard SRAM, 128KX8, | Hitachi | Discontinued
| W29EE011P-90Z | IC FLASH 1MBIT PARALLEL 32PLCC | Winbond Electronics | Discontinued
| SST39VF020 | 2Mb 2.7-3.6V Parallel Flash | MICROCHIP | In Production
| TN80C188EB20 | microprocessor | Intel | In Production
| 74HC373D | Octal D-type transparent latch; 3-state | NXP | In Production
| 74HC138D | 3-to-8 line decoder/demultiplexer; inverting | NXP | In Production
| DALLAS DS12C887 | DALLAS DS12C887 | DALLAS | In Production
| MAX232I | RS232 | TI | In Production
| HCT74AG | Dual D Flip-Flop with Set and Reset | Onsemi | In Production
| LM393 | Dual differential comparator | TI | In Production
| 74HC245 | Octal 3−State Noninverting Bus Transceiver | TI | In Production
82C55AM-10
| 74HC244D | Octal buffer/line driver; 3-state | NXP | In Production
| TC7109ACPL | Analog to Digital Converters - ADC 13 Bit Fast Recovery | Microchip Technology | In Production
| MM74C923N | IC ENCODER 20-KEY 1 X 9:4 20DIP | onsemi | In Production
83AH3VF
| TL074C | LOW-NOISE JFET-INPUT OPERATIONAL AMPLIFIER | TI
C1WS2702
TXD22231 IC
Most of the components are not available in India., We need to replace the Intel processor with a microcontroller. We need to replace through-hole components with SMD components. We need the old schematics PDF for reference.
Meril Remarks: Yes, Agreed , Kindly design New Main board PCB with Microcontroller

## Display and Incubator
Back
| Display |  | Incubation & Heater
Display to be replaced with Touch Screen, latest Display
| Meril Remarks: | Yes, this board will not be used for touch screen LCD, if new LCD has different connection, you need to design
This Coil is very reliable for big part heating, so we recommned to use same…

## New system Build
Back
| Proposed System : Block Diagram | Sr No | Key Items | Features | Remarks
|  | 1 | USB OTG | Allows the device to connect with USB peripherals, enhancing data transfer and compatibility.
|  | 2 | WIFI | Enables wireless connectivity for remote monitoring and control.
|  | 3 | BLE | Facilitates easy integration with mobile apps for seamless data access and device management.
|  | 4 | Bar-code Reader | Allows scanning of bar-codes for quick data entry or identification purposes.
|  | 5 | Touch Display | Provides a user-friendly interface for controlling and viewing device data directly.
|  | 6 | IOT Connectivity (Cloud Connectivity) | Stores data securely in the cloud for easy access, backup, and analysis over time.
|  | 7 | Thresholds, alerts etc | Sends alerts when specific parameters exceed set limits to ensure timely action.
|  | 8 | AI - Analysis | Uses artificial intelligence to analyze data and provide insights or recommendations. | Future Options
|  | 9 | Auto Stirrer | Automatic Stirring and Mixing Control with Variable Speed: Include a magnetic stirrer with variable speed control to precisely mix solutions as needed for different types of analyses | Future Options
|  | 10 | Ethernet | Provides a reliable wired network connection
|  | 11 | ADC - Resolution / Speed | High-Resolution ADC (Analog-to-Digital Converter): Converts analog signals from sensors into digital data with high accuracy.
|  | 12 | Production Test Features | ON Board LED- On board LED for Production testing | Future Options
|  | 13 | Meril Req. | All Connector for USB, Ethernet, RS232 need on PCB only, so we can interface PCB at backside of Base plate, so less cable assembly req.
|  | 14 | Meril Req. | Keep minimum Hardware calibration, need digitally (ADC Calibrations / Temp Calibration)
KEY HELIGHTS OF THE NEW SYSTEM - 1. Overall Cost of product will go down by 30 to 40% 2. EOL of the Product will be extended to next 10 to 15 Years 3. IOT Enabled / AI Enabled as needed (Provision) 4. Ease of Operation, Assembly and Maintenance 5. Touch Screen Display

## HW BreakDown
Back
Meril ClotQuant 2 HW Time Sheet
| Sr. No | Items | Parameters
| 1 | Research and Analysis | Product functional Research and Analysis
| 2 |  | proof of concept, and modeling
| 3 | Components selection | Micro-controller Selection
| 4 |  | ADC Selection
| 5 |  | Display Selection
| 6 |  | Other component Selection
|  | Hw design | Power Supply
| 7 |  | component symbol & footprint creation
| 8 |  | Schematic design & Review
| 9 |  | PCB components placement
| 10 |  | PCB design & Review
| 11 |  | BOM Creation & Review
| 12 |  | PCB gerber File generation & Review
Microcontroller Board
| 13 |  | component symbol & footprint creation
| 14 |  | Schematic design
| 15 |  | Schematic review
| 16 |  | PCB components placement & PCB design
| 17 |  | PCB Design review
| 18 |  | BOM Creation & Review
| 19 |  | PCB gerber File generation & Review
Connector Card
| 20 |  | components symbol & footprint creation
| 21 |  | Schematic design & Review
| 22 |  | PCB components placement & PCB design
| 23 |  | PCB Design review & BOM Review
| 24 |  | PCB gerber File generation & Review
Printer Driver Board
| 25 |  | components symbol & footprint creation
| 26 |  | Schematic design & Review
| 27 |  | PCB components placement & PCB design
| 28 |  | PCB Design review & BOM Review
| 29 |  | PCB gerber File generation & Review
| 30 | Mechanical Design | Mechanical Fitment module
| 31 |  | PCB mock up - from Mechanical model
| 32 | Pilot batch | component Sourcing
| 33 |  | PCB Fabrication
| 34 |  | Assembly
| 35 |  | Board Bring-Up
| 36 |  | 5 Unit Pilot batch

## WBS
Back
Key Activities
| Sr. No. | Milestones | Items | Descriptions | Activity | Output | Ownership | Efforts Weeks | Remark | Meril Remarks (IVD R&D)@19 Nov | Rezonet Remarks 21 Nov
| 1 | M1 | Specifications | - Specifications and Requirement document | - Specs and Requirements - Deliverables - Scope - Execution: Roles and Responsibilities - Schedules - Commercial - Tool, Software etc. - Environments - Stack (Licenses) Etc. (WiFi) - OS supports (Tiny RTOS) | - Spec Documents | Rezonet and Meril | 1 | - Finalise Specs - Unit COST - Ball park Figures - Requirments for 1st Release / 2nd Relase and so On
| 2 |  | Components Engineering | - Key Component Selections - Connectors / Interfaces | - BOM - Components EOL / Alternate - Vendors Options - Pricing / Cost Estimates etc - MOQ / SPQ etc | - Preliminary BOM | Rezonet |  | - Optimization - Tentative Costing - Volume - Target Cost etc
| 3 | M2 | Lib Creations | - Sch - PCB | - Lib Creations (Sch, PCB Both) | - Lib | Rezonet | 3
| 4 |  | System Partition | - Number of PCBs / Modules / Scalable and Modular approach | - CPU board (SOM) - Customised SOM / Off the shelves SOM - Customised Carrier Card | - System Architecture | Rezonet and Meril
| 5 |  | Schematics Creation | - Schematics creations for boards as per the System | Board 1 - CC | - Sch file for boards | Rezonet
| 6 | M3 | Mechanical Model | - Mechanical Design - Enclosure Design - Styling - Fitment | - Size - Enclosure - Modelling - Options - Custom design / Off the shelves - PC/ABS/Metal etc - Interfaces / Connectors - Fitments | - 3D model - Analysis | Rezonet and Meril | 1 | -Styling-Logo-Look AND Feel-Fitment requirements
| 7 |  | Layout / PCB Boards | - PCB Layout creations for boards as per the System | Board 1 - CC | - PCB Layout for boards | Rezonet | 4
| 8 | CaPEX At Actual | BOM Ordering / Procurement | Component Procurement |  | for 1 Proto and 4 Additional System Build | Rezonet | 1
| 9 | M4 | PCB Fabrication | - Typical time required for PCB Fabrications |  | - Bare PCBs | Outsourced | Outsource
| 10 |  | Board Assembly | - Typical time required for PCB Assembly |  | - Assembled PCBs | Outsourced
| 11 |  | Board re-spin if Any | - Update Sch / BOM / PCB |  | - New Revision if any | Rezonet | 3
| 12 |  | Board Bring up and Testing |  |  | - Tested PCBs | Rezonet | 4
| 13 | Next Phase | Precompliance | CE FCC Other compliance if any |  | - Compliance Problems issues if any | Rezonet and Meril | Next Phase
| 14 |  | Compliance | CE FCC Other compliance if any |  | - Certifications '- Results | Rezonet and Meril
| 15 | M5 | Module Level Code Development | Codes for Interfaces Like ADC, Sensor USB Eth Wifi Etc Documents/Logic etc |  | Modular Codes | Rezonet | 3 |  | 6 week timeline is Valid,if developing from scratch, Otherwise if using already available From Controller manufacturer requires less time. | We considered the interfaces with Individual Validations.
| 16 |  | Integration Code Testing | Documents/Logic/Codes etc |  | Integrated Codes | Rezonet | 3 |  | Need clarity for what kind of integration | Integration of Board Test application With interfaces ADC Interface, Hardware Integration and Testing as interfaces
| 17 |  | System Algo and Build | System level Application Build for the Unit |  | - System Testing | Rezonet and Meril | 0 | - Run the user applications / Mock the field Scenario | Existing algorithm is mixed with display, motor, and other temporary function, This activity has to done by Meril and if require support we will ask you... | OK Noted. Will remove this. From our List of activities
| 18 |  | Display App Development | App for the Display |  | Display App | Rezonet and Meril | 5 | Tablet / Display applications. | Need clarity, what kind of contribution Rezonet will provide for APP of the display. Does it include all menu and function for new display with front end and back-end? | Rezonet can take Care of complete App as needed for the Unit. May even need to work on Data packet Stricture.
| 19 | M6 | Testing / Integration Sample Testing | - Prepare Test Setup if any as per the user need |  | - Test setup | Rezonet and Meril | 2 |  | Who will prepare test setup? What task is distributed between Rezonet and meril? | - in House Testup as required for unit validation can be locally prepare by Rezonet. However Meril shall support for specific requirements like Tubes, Chemicals, Agents if any etc.
| 20 |  | Final Product Application Development if Any |  |  | - System Testing | Meril | Meril |  | Before final testing, need to mention about code optimization and bug fixing if found any And who will do it, Rezonet or meril? | For module / Interfaces level challenges, Rezonet would always be there. In case it is Application level, Meril may take care of. However support for the bug fixes will always be extended from Rezonet.
| 21 |  | System Testing |  |  | - System Testing | Meril | Meril | - Run the user applications / Mock the field Scenario
[6 empty] | Total Man Weeks |  | 30
[6 empty] | Man Months |  | 7.5
| Note - Printer Board and Printer Would be Provided by Meril Heater / Incubator shall be Provided by Meril Chemical / setup if any, Meril shall help Travel and Stay Expenses are at actual. Enclosure and Specialized Mechanical Details shall be Provided by |  |  |  |  | Man Month Efforts 1.5 Resources for 3 Months
Efforts Value
[6 empty] | Approximate Capex |  | Calculated At Actual 1+4 Nos of Protos
[6 empty] | Taxes as applicable | GST 18%
[6 empty] | Total | 0

## Microcontroller
Back
| Comparison table between the 80C188EB-20 and the NUCLEO-F767ZI (STM32F767ZIT6) |  |  | Comparison table between the NUCLEO-F722ZE and the NUCLEO-F767ZI (STM32F767ZIT6)
| Feature | 80C188EB-20 | NUCLEO-F767ZI (STM32F767ZIT6) | Feature | NUCLEO-F767ZI | NUCLEO-F722ZE
| Architecture | Intel 16-bit CISC (x86) | ARM Cortex-M7 32-bit RISC | Microcontroller | STM32F767ZI | STM32F722ZE
| Clock Speed | 20 MHz | 216 MHz | Core | ARM Cortex-M7 | ARM Cortex-M7
| Instruction Set | x86 | ARMv7-M | Clock Speed | Up to 216 MHz | Up to 216 MHz
| Integrated Memory | None (requires external memory) | 2 MB Flash, 512 KB SRAM | Flash Memory | 2 MB | 512 KB
| Memory Access | External memory using parallel bus | Internal memory; direct access | RAM | 512 KB | 256 KB
| Peripheral Interfaces | Parallel Bus, UART, Timers | SPI, I2C, CAN, UART, USB, Ethernet, SDIO, GPIOs | Package Type | LQFP144 | LQFP144
| Interrupt System | Legacy x86-style interrupt handling | Advanced NVIC (Nested Vectored Interrupt Controller) | Digital GPIO Pins | 114 | 114
| Voltage Levels | 5V | 3.3V | Analog Input Pins | 3 ADC (12-bit) | 3 ADC (12-bit)
| Pin Count | 84 pins (PLCC) | 144 pins (LQFP on STM32, 144-pin NUCLEO board) | UART Interfaces | 6 UARTs | 6 UARTs
| Development Ecosystem | Legacy tools (e.g., PL/M, assembly) | STM32CubeIDE, STM32CubeMX, HAL/LL libraries | SPI Interfaces | 6 SPI | 6 SPI
| Power Consumption | Higher | Lower | I2C Interfaces | 3 I2C | 3 I2C
| Power Modes | Limited | Multiple low-power modes (e.g., Sleep, Stop) | Timers | 14 (general, advanced, basic) | 14 (general, advanced, basic)
| Timers | Basic programmable timers | Multiple advanced timers with PWM, input capture, etc. | Ethernet MAC | Yes (with IEEE 1588 support) | Yes
| Communication | Legacy UART, parallel interface | SPI, I2C, UART, CAN, USB, Ethernet, SDIO | USB | USB OTG HS/FS | USB OTG HS/FS
| DMA | Not available | Multiple DMA channels | Cryptographic Support | Yes | No
| Floating-Point Support | No | Single and double-precision FPU | Floating Point Unit | Double Precision | Single Precision
| Target Applications | Legacy embedded systems | Modern high-performance systems | Connectivity | Advanced Ethernet and USB support | Basic Ethernet and USB support
| Package Type | PLCC | LQFP (on NUCLEO board: 144-pin headers) | Power Supply | 3.3V/5V via USB or external source | 3.3V/5V via USB or external source
| Debugging Tools | Limited | Advanced debugging (SWD, JTAG, ST-Link) | Board Size | Larger (dimensions vary slightly) | Slightly smaller
| Community Support | Limited | Extensive community and documentation | Use Case | High-performance, advanced IoT and real-time applications | Mid-range embedded systems and control applications
| Cost | 3000 INR | 2000 INR
| Software Support | Legacy (PL/M, assembly) | Modern C/C++ libraries, middleware support
| Expandability | Requires external memory and peripherals | Arduino-compatible and ST morpho headers for prototyping

## 80C188EB-20
Back
Existing Processor Pinout & Architecture - 80C188EB-20
| Sr No | PIN OUT
| 1 | VCC
| 2 | RD
| 3 | WR
| 4 | ALE
| 5 | S2
| 6 | S1
| 7 | S0
| 8 | DEN
| 9 | GND
| 10 | SL
| 11 | BHE
| 12 | HLDA
| 13 | HOLD
| 14 | BUSY/TEST
| 15 | LOCK
| 16 | DT/R
| 17 | READY
| 18 | GCS7
| 19 | P1.7/GCS7
| 20 | P1.6/GCS6
| 21 | P1.5/GCS5
| 22 | P1.4/GCS4
| 23 | P1.3/GCS3
| 24 | P1.2/GCS2
| 25 | P1.1/GCS1
| 26 | P1.0/GCS0
| 27 | GCS6
| 28 | GCS0
| 29 | LCS
| 30 | UCS
| 31 | INT0
| 32 | INT1
| 33 | INT2/TMR0
| 34 | INT3/TMR1
| 35 | P2.3/STNT1
| 36 | P2.2/BCLK1
| 37 | P2.1/TXD1
| 38 | P2.0/RXD1
| 39 | P2.4/CTS1
| 40 | RXD0
| 41 | TXD0
| 42 | TCLK0
| 43 | TOUT
| 44 | CSOUT
| 45 | PCS5
| 46 | PCS4
| 47 | PCS3
| 48 | PCS2
| 49 | PCS1
| 50 | RESET
| 51 | PREBOOT
| 52 | NMI
| 53 | GND
| 54 | PCS0
| 55 | PCS0
| 64 | A8
| 65 | A9
| 66 | A10
| 67 | A11
| 68 | A12
| 69 | A13
| 70 | A14
| 71 | A15
| 72 | A16
| 73 | A17
| 74 | A18
| 75 | A19/ONSE
| 56 | AD0
| 57 | AD1
| 58 | AD2
| 59 | AD3
| 60 | AD4
| 61 | AD5
| 62 | AD6
| 63 | AD7
| 76 | AD18
| 77 | AD17
| 78 | AD16
| 79 | AD15
| 80 | AD14
| 81 | AD13
| 82 | AD12
| 83 | AD11
| 84 | AD10

## BD + PowerSch
Back
| Block - Dia : System | Block - Dia - System Power Scheme

## STM32F767ZIT6mapping
Back
| Pin Number | Pin Name | Primary Function | ClotQuant2 mapping
| 1 | PE2 | GPIO/Alternate Function
| 2 | PE3 | GPIO/Alternate Function
| 3 | PE4 | GPIO/Alternate Function
| 4 | PE5 | GPIO/Alternate Function
| 5 | PE6 | GPIO/Alternate Function
| 6 | VBAT | Backup Battery Supply
| 7 | PC13 | GPIO/RTC Tamper-1 |  | RTC
| 8 | PC14 | GPIO/OSC32_IN
| 9 | PC15 | GPIO/OSC32_OUT
| 10 | PF0 | GPIO/OSC_IN
| 11 | PF1 | GPIO/OSC_OUT
| 12 | PF2 | Reset Input
| 13 | PF3 | GPIO/ADC Input
| 14 | PF4
| 15 | PF5 | GPIO/ADC Input
| 16 | VSSA | Analog Ground
| 17 | VDD | Power Supply
| 18 | PF6
| 19 | PF7
| 20 | PF8
| 21 | PF9
| 22 | PF10
| 23 | PH0/OSC IN |  |  | OSC
| 24 | PH1/OSC OUT
| 25 | NRST
| 26 | PCO
| 27 | PC1 | ETH-MDC |  | ETH
| 28 | PC2
| 29 | PC3 |  |  | PIPETTE
| 30 | VDD | Power Supply
| 31 | VSS | GND
| 32 | VREF
| 33 | VDDA | Power Supply
| 34 | PA0 | UART4 TX
| 35 | PA1 | ETH-REF-CLK
| 36 | PA2 | ETH-MDIO
| 37 | PA3
| 38 | VSS | GND
| 39 | VDD | Power Supply
| 40 | PA4
| 41 | PA5 | SPI1 SCK |  | ADC SPI
| 42 | PA6 | SPI1-MOSI
| 43 | PA7 | ETHCRC-DV |  | ETH
| 44 | PC4 | ETH-RXD0
| 45 | PC5 | ETH-RXD1
| 46 | PB0 | GPIO/Alternate Function
| 47 | PB1 | GPIO
| 48 | PB2 | GPIO
| 49 | PF11 | GPIO
| 50 | PF12 | GPIO
| 51 | VSS | GND
| 52 | VDD | Power Supply
| 53 | PF13 | GPIO
| 54 | PF14 | GPIO
| 55 | PF15 | GPIO
| 56 | PG0 | GPIO
| 57 | PG1 | GPIO
| 58 | PE7 | GPIO
| 59 | PE8 | GPIO
| 60 | PE9 | GPIO
| 61 | VSS | GND
| 62 | VDD | Power Supply
| 63 | PE10 | GPIO
| 64 | PE11 | GPIO
| 65 | PE12 | GPIO
| 66 | PE13 | GPIO
| 67 | PE14 | GPIO
| 68 | PE15 | GPIO
| 69 | PB10 | GPIO
| 70 | PB11 | GPIO/Alternate Function | ETH-TX-EN
| 71 | VCAP
| 72 | VDD | Power Supply
| 73 | PB12 | GPIO/Alternate Function | ETH-TXD0
| 74 | PB13 | GPIO/Alternate Function | ETH-TXD1
| 75 | PB14 | USB DM |  | USB DEVICE
| 76 | PB15 | GPIO-DP
| 77 | PD8 | GPIO
| 78 | PD9 | GPIO
| 79 | PD10 | GPIO
| 80 | PD11 | GPIO
| 81 | PD12 | GPIO
| 82 | PD13 | GPIO
| 83 | VSS | GND
| 84 | VDD | Power Supply
| 85 | PD14 | GPIO
| 86 | PD15 | GPIO
| 87 | PG2 | GPIO
| 88 | PG3 | GPIO
| 89 | PG4 | GPIO
| 90 | PG5 | GPIO
| 91 | PG6 | GPIO
| 92 | PG7 | GPIO
| 93 | PG8 | GPIO
| 94 | VSS | Ground
| 95 | VDD | Power Supply
| 96 | PC6 | BUZZER
| 97 | PC7 | GPIO/Alternate Function
| 98 | PC8 | GPIO/Alternate Function
| 99 | PC9 | GPO
| 100 | PA8 | GPI
| 101 | PA9 | USB-OTG-FS-VBUS |  | USB
| 102 | PA10 | USB-OTG-FS-ID
| 103 | PA11 | USB-OTG-FS-DM
| 104 | PA12 | USB-OTG-FS-DP
| 105 | PA13 | GPIO/Alternate Function
| 106 | VCCA
| 107 | VSS | GND
| 108 | VDD | Power Supply
| 109 | PA14 | GPIO/Alternate Function
| 110 | PA15 | GPIO/Alternate Function
| 111 | PB10 | GPIO/Alternate Function
| 112 | PC11 | UART4 RX
| 113 | PC12 | UART5 TX
| 114 | PD0 | GPIO/Alternate Function
| 115 | PD1 | GPIO/Alternate Function
| 116 | PD2 | UART5 RX
| 117 | PD3 | GPIO/Alternate Function
| 118 | PD4 | GPIO/Alternate Function
| 119 | PD5 | GPIO/Alternate Function
| 120 | VSS | GND
| 121 | VDD | Power Supply
| 122 | PD6 | GPIO/Alternate Function
| 123 | PD7 | SPI1-MOSI |  | SPI ADC
| 124 | PG9 | GPIO/Alternate Function
| 125 | PG10
| 126 | PG11 | GPO | CGS4 | Heator
| 127 | PG12 | GPO | CGS5
| 128 | PG13 | GPO | CT
| 129 | PG14 | GPO | PBUSY | PRINTER
| 130 | Vss | GND
| 131 | VDD | Power Supply
| 132 | PG15 | GPO | STB
| 133 | PB3 | GPO | PD0
| 134 | PB4 | GPO | PD1
| 135 | PB5 | GPO | PD2
| 136 | PB6 | GPO | PD3
| 137 | PB7 | GPO | PD4
| 138 | BOOT0
| 139 | PB8 | GPO | PD5
| 140 | PB9 | GPO | PD6
| 141 | PE0 | GPO | PD7
| 142 | PE1 | GPI | ACK
| 143 | PDR
| 144 | VDD | Power Supply

## ADC
Back
TC7109ACPL- Dual-Slope ADC - Existing ADC

## Memory
Back
Internal Memory (STM32F767ZIT)
| Sr No | Memory type | Size | Use
| 1 | flash | 2 Mbytes | Stores the application firmware and persistent data.
| 2 | SRAM | 512 Kbytes | Stores variables, stack, and runtime data for active processing
| 3 | Instruction Cache | 16 KB | Speeds up program execution by caching instructions for quick access.
| 4 | Data Cache | 16 KB | Accelerates data access during runtime by caching frequently used data.
External Memory (STM32F767ZIT)
| Sr No | Memory type | Size | Use | Part no
| 1 | SDRAM | 64 Mbit | Expands memory for large datasets, multimedia processing, or advanced algorithms. | AS4C4M16SA-7TCN | Parallel
| 2 | EEPROM | 512Kbit | Stores non-volatile data such as configurations or calibration parameters. | 24LC512-I/SN | I2C

## Eth_phy
Back
Ethernet Phy
Specifications
| Brand: | Microchip Technology
| Data Rate: | 10 Mb/s, 100 Mb/s
| Duplex: | Full Duplex, Half Duplex
| Height: | 0.85 mm
| Interface Type: | MDI-X, RMII
| Length: | 4 mm
| Maximum Operating Temperature: | + 85 C
| Minimum Operating Temperature: | 0 C
| Moisture Sensitive: | Yes
| Mounting Style: | SMD/SMT
| Number of Transceivers: | 1 Transceiver
| Package/Case: | QFN-24
| Packaging: | Tray
| Product: | Ethernet Transceivers
| Product Type: | Ethernet ICs
| Series: | LAN8720A
| Standard: | 10BASE-T, 100BASE-TX
| Subcategory: | Communication & Networking ICs
| Supply Current - Max: | 21 mA
| Supply Voltage - Max: | 1.26 V
| Supply Voltage - Min: | 1.14 V
| Width: | 4 mm

## Design Decisions
Back
| Sr No. | Features | Descriptions | Yes / No | Nos. | Comments | Meril - Remark
| 1 | USB OTG | Allows the device to connect with USB peripherals, enhancing data transfer and compatibility. | Yes | 2 Nos. | 1 - for PEN Driver 2 - Display Interface (Internal)
| 2 | WIFI | Enables wireless connectivity for remote monitoring and control. | Yes | 1 Nos.
| 3 | BLE | Facilitates easy integration with mobile apps for seamless data access and device management. | Yes | 1 Nos. | Provision as possible
| 4 | Bar-code Reader | Allows scanning of bar-codes for quick data entry or identification purposes. | Yes | 1 Nos. | RS232 Based. Details shall be provided by Meril
| 5 | Touch Display | Provides a user-friendly interface for controlling and viewing device data directly. | Yes | 1 Nos. | Display Options 1. Tablets (Via USB) 2. HDMI Based Display 3. TFTP Display
| 6 | Thresholds, alerts etc | Sends alerts when specific parameters exceed set limits to ensure timely action. | Yes |  | It would be used as a Warning / Information
| 7 | Auto Stirrer | Automatic Stirring and Mixing Control with Variable Speed: Include a magnetic stirrer with variable speed control to precisely mix solutions as needed for different types of analyses | Yes |  | Future Options
| 8 | Ethernet | Provides a reliable wired network connection | Yes | 1 Nos. | 10/100 Ethernet support
| 9 | ADC - Resolution / Speed | High-Resolution ADC (Analog-to-Digital Converter): Converts analog signals from sensors into digital data with high accuracy. | Yes | 1 Nos. | For Temp monitoring 12 Bit / 100ksps / SPI ADCs
| 10 | Production Test Features | ON Board LED- On board LED for Production testing | Yes |  | Future Options / May need more details from Meril
| 11 | Connectors on Back side Panel | All Connector for USB, Ethernet, RS232 need on PCB only, so we can interface PCB at backside of Base plate, so less cable assembly req. | Yes |  | Connectors would be aligned to Panel
| 12 | Calibrations | Keep minimum Hardware calibration, need digitally (ADC Calibrations / Temp Calibration) | Yes |  | Software based provision for calibration and Records.
| 13 | RTC | Internal RTC to the controllers would be used, required battery backed shall be provided | Yes |  | Battery Back back provided on board
| 14 | Buzzer / Speaker | Buzzer would be provided on the system, Rezonet would select most reliable buzzer to take of existing Problems. | Yes | 1 Nos. | Buzzer for Alarms and Indications.
| 15 | Printer Interface | Meril would Provide the Printer Interface HW details to be used for new system build | Yes |  | Parallel Printer Interface
| 16 | Heater Elements | New System would use the existing Heater system, the details of the Heater, including interface details shall be available from Meril | Yes |  | To use existing Heater system
| 17 | Memory | System shall be provided on board additional memory like I2C - Flash to store calibration data SDRAM - Only in case it is must.
| 18 | HDMI Support | HDMI support would be provided in case HDMI Display to be used | Yes | 1 Nos | HDMI to be used in case HDMI display to be used
| 19 | RS232 | RS232 to be used as a debug interface | Yes | 1 Nos | TO be used for debug.
20
21
22
23
24
25
26
27
28